## Sheet1
Pages | Status | Assigend To | Start Date | Tentative End date | Dependent DLL 1 | Dependent DLL 2 | Dependent DLL 3 | Dependent DLL 4 | Dependent DLL 5 | Dependent DLL 6 | Dependent DLL 7 | Application Dependent | Application Dependent
Master Data
1. Area/SubArea | Done
2. Defect-Repair Mapping | Not Opened | Naresh | 2018-12-20 |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
3. CallType-CallAt Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
4. Product-CallType Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
5. Product-CallType-Symptom Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
6. Symptom-Defect Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
7. RR Incentive Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
8. Model-Part DateClouser Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
9. FG Pairing | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
10. Factory Esclation | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
11. Liquidate Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
11. Liquidate Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
13. Dealer Distributor Mapping List | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
14. Franchisee | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
15. Technician Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
16. Add/View cities | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
17. Branch Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
18. Create/Edit Menu | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
19. Area Allocation/Reallocation NEW | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
20. Refresh XML | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
21. Brand Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
22. Product Category | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
23. Product Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
24. Brand Product Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
25. Model Category | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
26. Model Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
27. BM RM Contract List | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
28. Part Category | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
29. Part Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
30. Part Model Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
31. Alternate Part Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
32. Bin Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
33. Reason Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
34. Part Category Bin Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
35. Job Charge Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
36. Vendor Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
37. Tax Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
38. Local/Upcountry Mapping Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
39. Payout Matrix | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
40. Edit ASI Name | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
41. City Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
42. Dealer Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
43. Service Tax Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
44. BSM Contact List | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
45. Call Type Wise Allocation | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
46. FOC Approver Authority | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
47. Add ASC in Call Type Wise Allocation | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
48. Plant Product Brand Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
49. Upload A- Class Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
50. Complaint Description | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
51. Part Sub Category | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
52. Part Category-Sub Category Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
53. Part Sub Category-Sub Category Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
54. Part Category-Factory Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
55. PDI Contact List | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
56. PDI Brand-Group Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
57. PDI Action Mail Matrix | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
58. TS Identification Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
59. TS Branch Activation Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
60. Branch Part Category Issued Flag Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
61. Master-Branch & SAP Branch Map | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
62. EW Plan Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
63. EW Plan Model Mapping Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
64. Master-VOC Transit Time | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
65. Master-VOC Screen Controller | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
66. Master-VOC SE Allocation Slab Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
67. Master-Branch Wise VOC Activation | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
68. Supervisor Technician Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
69. Product Wise Service-Duration Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
70. Technician Skill Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
71. Technician Pincode Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
72. Communication Message Master | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
73. ASC Holiday Details | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
74. Image-Document Type Master Mapping | Not Opened | Naresh |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
| Not Opened |  |  |  | DAL.dll | GMM.dll | GMM_BO.dll | ExcelGeneratol.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
1. Transaction Index |  |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
1. Call Registration | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
2. Call Updation | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
3. Manual Allocation | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
4. Wrong Allocation | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
5. Call Cancel | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
6. Service Engineer Allocation | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
7. Service Engineer ReAllocation | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
8. Customer Invoice | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
9. Outbound TS Call Search | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
[5 empty] | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
2. Reports Index |  |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
1. AMC Report | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
2. Reminder Summary | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
3. Call Report | need to be discussed |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
4. Technical Call Analysis | error | Vipul |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
5. Call Report Part Pending | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
6. DSR | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
7. DSR New | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
8. CNA Call Reports | need to be discussed |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
9. Customer DSR | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
10. Pre-Sales DSR | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
11. Open Pending With Ageing | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
12. Summary Response Time | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
13. Summary TAT | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
14. Area Allocation Report | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
15. All India Open Pending With Ageing | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
16. Branch Call Count | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
17. Branch Call Summary | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
18. All India Call Summary | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
19. Branch Wise Open Pending With Ageing | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
20. Call Productivity | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
21. Archived Data Call Report | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
22. Closed Call Report | Done |  |  |  | DAL.dll |  |  |  | ExceptionLog_CS.dll | ExceptionManagement.dll | GRFMessages.resources.dll | GMM Application
23. RDLC Generator | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
24. Ageing Report | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
25. Transaction Ledger Report | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
26. Claim Report | Done |  |  |  | DAL.dll | [6 empty] | GMM Application
27. TCR Report | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
28. Stock Report | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
29. Customer Invoice Report | error | Vipul |  |  | DAL.dll | ReportUtility.dll | GenReportWeb.dll | GenReportBO.dll | ExcelGenrator.dll | ExceptionLog_CS.dll | ExceptionManagement.dll | GMM Application
30. Purchase Order Report | Done |  |  |  | DAL.dll
31. MSL Report | Done |  |  |  | DAL.dll
32. ASC/DSC Productivity | Done |  |  |  | DAL.dll
33. KPI Analysis Report | Done |  |  |  | DAL.dll
34. Open Pending With Ageing Brand Priority Wise | Done |  |  |  | DAL.dll
35. Technician Performance Report | Done |  |  |  | DAL.dll
36. Warehouse DSR | Done |  |  |  | DAL.dll
37. MFG Serial No. Wise Ledger Report | Done |  |  |  | DAL.dll
38. Extended Warranty Sales Report | Done |  |  |  | DAL.dll
39. Extended Warranty AMC Cost Report | Done |  |  |  | DAL.dll
40. Extended Warranty Completed Calls Detailed Report | Done |  |  |  | DAL.dll
41. Extended Warranty Plan-wise Report | Done |  |  |  | DAL.dll
42. VOC-Commitment Success fail Summary Report | Done |  |  |  | DAL.dll
43. Re-send SMS Report | Done |  |  |  | DAL.dll
44. VOC-Complaint date to commitment date>21 days Report | Done |  |  |  | DAL.dll
45. VOC-Commitment Failure Report | Done |  |  |  | DAL.dll
46. VOC-CWH & Store Performance Summary | Done |  |  |  | DAL.dll
47. MFG Serial No. Wise Report | Done |  |  |  | DAL.dll
48. Technician Responsibility Report | Done |  |  |  | DAL.dll
DAL.dll
3. Print Index |  |  |  |  | DAL.dll
1. Job Card | error | Vipul |  |  | DAL.dll
4. User Management Index |  |  |  |  | DAL.dll
1. Create/Edit | Done |  |  |  | DAL.dll
2. Change Password | Done |  |  |  | DAL.dll
3. Login Report | Done |  |  |  | DAL.dll
4. Reset Password | Done |  |  |  | DAL.dll
5. Update User Status | Done |  |  |  | DAL.dll
5. AMC Index | Done |  |  |  | DAL.dll
1. AMC Registration | Done |  |  |  | DAL.dll
2. AMC Search | Done |  |  |  | DAL.dll
3. AMC Update | Done |  |  |  | DAL.dll
4. AMC Form PO Approval | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
5. AMC Form PO Receipt | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
6. AMC Form Allocation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
7. AMC Form Cancellation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
8. AMC Form Return | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
6. SMS Service Index |  |  |  |  | DAL.dll
1. Customer Response | Done |  |  |  | DAL.dll
2. Re-Send SCode | Done |  |  |  | DAL.dll
3. SMS Log | Done |  |  |  | DAL.dll
7. Inventory Index |  |  |  |  | DAL.dll
1. Inventory Initialization | Done |  |  |  | DAL.dll
2. Inventory Adjustment | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
3. Rental Allocation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
4. Rental Return(OK) | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
5. Rental Return(Defected) | error |  |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
8. Purchase Order Index | Done |  |  |  | DAL.dll
1. PO Generation | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
2. Reprocess Order | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
3. Close PO | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
4. PO Approval | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
9. Challan Index | Done |  |  |  | DAL.dll
1. Challan Generation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
2. Reprocess Generation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
3. Close Generation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
4. Reopen Generation | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
10. Receipt Index | Done |  |  |  | DAL.dll
1. Receipt | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
11. Claim Processing Index | Done |  |  |  | DAL.dll
1. Confirm Validated Call | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
2. View Claim | Done |  |  |  | DAL.dll
3. Claim Approval | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
4. View Validated Call | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
5. View Claim | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll | webUtils.dll
6. Call Validation Process Recording | Done |  |  |  | DAL.dll
12. Views Index |  |  |  |  | DAL.dll
1. ASC Ledger | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
2. RRR123 Deviating Calls | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
3. RRR123 ASC RRIncentive | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
4. RRR123 Completed and deviating Calls | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
5. FG Pairing | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
6. AMC Punch Report | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
7. Call Type Wise Area Allocation Report | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
8. SSNO AND DOP Tracking | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
9. SSNO AND DOP Updated | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
10. VPOT Files | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
11. Bar Code Scan | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
12. Bar Code Invoice | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
13. Liquidate Master | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
14. Branch Inventory | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
15. Claim Acknowledgement | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
16. Asc Stock | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
17. Invoice Sales | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
18. Direct Sales | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
19. PO Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
20. Challan Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
21. Challan Details History | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
22. Tech Ledger | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
23. Inventory Initialization | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
24. Tech Stock | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
25. Part Search | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
26. Alternate Part Search | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
27. Service BOM | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
28. Print Return(OK) Slip | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
29. Print Return(Defected) Slip | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
30. Print Allocation Slip | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
31. Customer Invoice | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
32. A-Class Mapping | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
33. A-Class Upload Rejection | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
34. Fault Details |  | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
35. Action Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
36. Section Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
37. ASI Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
38. Re-Open Calls Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
39. Franchisee Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
40. AMC Modified Data | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
41. BCC Job Charge Master | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
42. Ext Warranty AMC Report | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
43. SAP Stock | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
44. Part Wise Maker Wise MFGSSN Validation Logic | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
45. Maker Week Code Master | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
46. FG Pairing-Category Wise View | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
47. Search Part Serial Number | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
48. ASC PART MFG SERIAL NO. MAP | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
49. MFG Serial No. With Pending Calls | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
50. Serial Number Wise Extended Warranty Plan Details | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
51. Presale Calls with Photos | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
52. Haze Customer Profile | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
53. FG-Panel Serial No | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
54. Call Update Images Log | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
13. SMS Call Registration Index |  |  |  |  | DAL.dll
1. View Reopen Calls | error | Vipul |  |  | DAL.dll | GenericView.dll | GenLovBo.dll | GMM.dll | GMM_BO.dll | GMDatePicker.dll | CheckSum.dll | GenericView Application
14. CSO Reports Index |  |  |  |  | DAL.dll
1. AMC Calls | Done |  |  |  | DAL.dll
2. Get FCR/ Cancel Details | Done |  |  |  | DAL.dll
3. Cancel Calls Count | Done |  |  |  | DAL.dll
4. Cancel Calls Data | Done |  |  |  | DAL.dll
5. Dashboard | Done |  |  |  | DAL.dll
6. Pagepoint Calls | Done |  |  |  | DAL.dll
7. Userwise Calls | Done |  |  |  | DAL.dll
8. DGWorld Calls | Done |  |  |  | DAL.dll
9. OW Call Analysis | Done |  |  |  | DAL.dll
15. TCR Index | Done |  |  |  | DAL.dll
1. TCR Allocation | Done |  |  |  | DAL.dll
2. TCR PO Approval | Done |  |  |  | DAL.dll
3. TCR Return | Done |  |  |  | DAL.dll
4. TCR Receive | Done |  |  |  | DAL.dll
5. TCR Cancel | Done |  |  |  | DAL.dll
16. Bulk Upload Index |  |  |  |  | DAL.dll
1. Upload Claims | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
2. Upload RR Incentive Master | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
3. Upload Soft Closed Calls | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
4. Upload FG Pairing | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
5. Upload Model Part Closure Date | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
6. Upload Payout Category Mapping | Done |  |  |  | DAL.dll
7. Upload SSNO & DOP | Done |  |  |  | DAL.dll
8. Upload Adujustment | Done |  |  |  | DAL.dll
9. Upload Inv Initialization | Done |  |  |  | DAL.dll
10. Upload LiquidateSet | Done |  |  |  | DAL.dll
11. Dealer-Distributor Mapping | Done |  |  |  | DAL.dll
12. Upload Model | Done |  |  |  | DAL.dll
13. Upload Set Serial No | Done |  |  |  | DAL.dll
14. Upload Dispatch Dtl | Done |  |  |  | DAL.dll
15. Upload Part | Done |  |  |  | DAL.dll
16. Upload SBOM | Done |  |  |  | DAL.dll
17. Upload Rejected/ Approved Calls | Done |  |  |  | DAL.dll
18. Upload Unfreeze Liquidated Calls | Done |  |  |  | DAL.dll
19. Upload Bulk Calls Status | Done |  |  |  | DAL.dll
20. Alternet Part Upload | Done |  |  |  | DAL.dll
21. Local-Upcountry Mapping Upload | Done |  |  |  | DAL.dll
22. Area Allocation-Reallocation Upload | Done |  |  |  | DAL.dll
23. Upload SSNO/DOP/Model against HCP NO | Done |  |  |  | DAL.dll
24. Upload Model/DOP against SSNo | Done |  |  |  | DAL.dll
25. Upload Ext Warranty Ref# | Done |  |  |  | DAL.dll
26. Branch Area Allocation-Reallocation Upload | Done |  |  |  | DAL.dll
27. Upload Maker Week Code Master | Done |  |  |  | DAL.dll
28. Upload Part Wise Maker Wise MFGSSN Validation Logic | Done |  |  |  | DAL.dll
29. Upload Call Wise Part Wise Bypass Validation Logic | Done |  |  |  | DAL.dll
30. Upload Call From- Master | Done |  |  |  | DAL.dll
31. Upload Part Code Wise MFG-SrNo Wise Complaint Number | Done |  |  |  | DAL.dll
32. Upload Set Serial No Wise Compliant against DOA | Done |  |  |  | DAL.dll
33. Upload to Change Invoice Charges | Done |  |  |  | DAL.dll
34. Upload Issue Material Details | Done |  |  |  | DAL.dll
35. Upload Franchisee-Part Code-MFGSrNo Map | Done |  |  |  | DAL.dll
36. Upload Issue Material Details Asi | Done |  |  |  | DAL.dll
37. Upload to Change Svc Type | Done |  |  |  | DAL.dll
38. Upload EW Plan Model Mapping | Done |  |  |  | DAL.dll
39. Upload VOC Escalated Complaints | Done |  |  |  | DAL.dll
40. Upload VOC CWH Data | Done |  |  |  | DAL.dll
41. Upload to Change Open Cell SrNo | Done |  |  |  | DAL.dll
42. Upload VOC STORE Data | Done |  |  |  | DAL.dll
43. Upload Technician Skill Mapping | Done |  |  |  | DAL.dll
44. Upload Technician Pincode Mapping | Done |  |  |  | DAL.dll
45. Update Franchisee in Bulk | Done |  |  |  | DAL.dll
46. Upload to change MFG SSNo in closed call | Done |  |  |  | DAL.dll
47. Bulk Upload-CallRegistration | Done |  |  |  | DAL.dll
48. Bulk Upload-Job Charge Master | Done |  |  |  | DAL.dll
DAL.dll
17. Service Support Index |  |  |  |  | DAL.dll
1. Invoice Cancel | Done |  |  |  | DAL.dll
18. PDI Index |  |  |  |  | DAL.dll
1. Pending Calls-PDI 1.6 | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
2. Pending Calls-PDI 1.7 | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll
3. PDI-Not Belong To Me | error | Vipul |  |  | DAL.dll | VGInventoryBO.dll
19. PDI Report Index |  |  |  |  | DAL.dll
1. Pre Sale Call Summary Report | Done |  |  |  | DAL.dll
2. Pre Sale Approval Call Report | Done |  |  |  | DAL.dll
3. Pending Pre-Sale Approval Report | Done |  |  |  | DAL.dll
4. Liquidation and Repairing Cost Report | Done |  |  |  | DAL.dll
20. TS Report Index |  |  |  |  | DAL.dll
1. TS IB Closure Dashboard | Done |  |  |  | DAL.dll
2. TS OB Closure Dashboard | Done |  |  |  | DAL.dll
3. TS IB/OB Closure Report | Done |  |  |  | DAL.dll
21. Technician HelpDesk Index |  |  |  |  | DAL.dll
1.Exploded View Details | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
22. Knowledge Bank Index |  |  |  |  | DAL.dll
1.Technical Manual Details | error | Naresh |  |  | DAL.dll | VGInventoryBO.dll
23. Mobile Report Index |  |  |  |  | DAL.dll
1.Call Register Data Summary | Done |  |  |  | DAL.dll
24. Service Manual
25. Bulletin
26. .Logout

## Sheet2
Sno | DLL Files | Status | Status | Start Date | Tentative End date | Name
1 | Genric View.dll | Partially Decompiled | Done
2 | Dal.dll | Partially Decompiled | Done
3 | CheckSum.dll | Partially Decompiled | Process | 2018-12-20 | 2018-12-21 | Vipul
4 | Excelgenerator.dll | Partially Decompiled | Process | 2018-12-24 | 2018-12-26 | Vipul
5 | GMM.DLL | Partially Decompiled | Done
7 | GenLovBo.dll | Partially Decompiled | Process | 2018-12-27 | 2018-12-28 | Vipul
8 | GenReportBo.dll | Partially Decompiled | Process | 2018-12-31 | 2019-01-04 | Vipul
9 | LovBO.dll | Partially Decompiled |  | 2019-01-07 | 2019-01-08 | Vipul
10 | SecurityBO.dll | Partially Decompiled | Done
11 | GMM_BO.dll | Partially Decompiled | Process | 2018-12-20 | 2018-12-21 | Naresh
12 | ExceptionManagement.dll | Partially Decompiled |  | 2018-12-24 | 2018-12-26 | Naresh
13 | ExceptionLog_CS.dll | Partially Decompiled |  | 2018-12-27 | 2018-12-28 | Naresh
14 | GRFMessages.resources.dll | Partially Decompiled | Process | 2018-12-31 | 2019-01-02 | Naresh
15 | ReportUtility.dll | Partially Decompiled | Process | 2019-01-03 | 2019-01-07 | Naresh
16 | GenReportWeb.dll | Partially Decompiled | Process | 2019-01-08 | 2019-01-10 | Naresh
17 | GenReportBO.dll | Partially Decompiled | Process | 2019-01-11 | 2019-01-14 | Naresh
20 | VGInventoryBO.dll | Partially Decompiled | Process | 2019-01-09 | 2019-01-11 | Vipul
21 | webUtils.dll | Partially Decompiled | Process | 2019-01-12 | 2019-01-14 | Vipul
22 | GMDatePicker.dll | Partially Decompiled | Process | 2019-01-15 | 2019-01-16 | Vipul
23 | GMM Application | Master Depandancy | Process | 2018-12-20 | 2018-12-28 | Naresh
24 | Generic Application | Service | Done
25 | Generic Service | Service | Done
26 | GMMLOV | Service | Done
27 | IGM | Service | Done

## Sheet3
1. List of Services
Sno | Services | Status
1 | Generic View | Not working
2 | GenViewBo | Not working
3 | GMMLovService | Not working
4 | LovBo | Not working