## 20.11.2018
MODULES & OBSERVATIONS | USERS | Status | Responsibility | BSL Remarks_20.11.2018 | Status
PHASE-I |  | Heading
Users Management | Users | Heading
User not created in Vendor portal for supplier & Buyer | A | Done |  | ok
No mandatory field indicated while creating users on UAT | A | Done |  | ok
Manage Roles module is not justified or even not under stable on UAT | A | Done |  | ok
Buyer Association not working | A | Done |  | ok
Masters Module | Users | Heading
No option to create or change master data for Material & Vendors | A | Data is from SAP so no scope for change or modify the exsting data. Need to discuss |  | Done through FTP, otherwise system data and ftp data get variations
Buyer Module | Users | Heading
Not working in Admin and no file is going to open in this module | A | Done |  | ok
PHASE-II |  | Heading
Supplier Management | Users | Heading
No data available for testing - pending from BSL side coz no file send from SAP to FTP server | A | No Action; Need to discuss |  | Data still not uploaded on portal | Done
ECN - Under Testing at BSL end | A,B,S | Done |  | ok but need to discuss with R & D
Material Management | Users | Heading
Calendar - No data Available | A,B,S | Done | Anoop | Need to discuss
Packaging Standard Upload | Users | Heading
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No drop down list of suppliers search - we want search option mentioning supplier code and supplier name (As shown in SOW) | A,B | Done | Anoop | Supplier Code with Supplier name required to search data | Done
No drop down list of material search and linked with P.O. | S | Done |  | ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,B,S | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B,S | No Action; Need to discuss |  | supplier code & name required
Supplier Sourcing Declaration | Users | Heading
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No drop down list of suppliers search - we want search option mentioning supplier code and supplier name (As shown in SOW) | A,B | Done | Anoop | Supplier Code with Supplier name required to search data | Done
No drop down list of material search and linked with P.O. | S | Done |  | ok
Material code never repeated for single supplier (E.g. Repeated in A10001) | S | Done | Anoop | ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,S | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B | No Action; Need to discuss |  | supplier code & name required
Supplier Capacity Declaration | Users | Heading
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No drop down list of suppliers search - we want search option mentioning supplier code and supplier name (As shown in SOW) | A,B | Done | Anoop | Supplier Code with Supplier name required to search data | Done
No drop down list of material search and linked with P.O. | S | Done |  | ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,S | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B | Done |  | supplier code & name required
Quality Certificate Upload | Users | Heading
Not as per the SOW, no options available to upload document as per the requirement documents | A,B,S | Done | Anoop | ok
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No drop down list of suppliers search - we want search option mentioning supplier code and supplier name (As shown in SOW) | A,B | Done | Anoop | Supplier Code with Supplier name required to search data | Done
No drop down list of material search and linked with P.O. | S | Done |  | ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,S | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B | No Action; Need to discuss |  | supplier code & name required
File upload without selecting supplier | A,B,S | Done |  | ok
Fortnight plan | Users | Heading
No option to upload fortnight plan monthly | A,B | Out of Scope |  | Ok
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No need of supplier search and material search on portal - Common data for all suppliers | A,B,S | Done | Priyanshu | Ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,B | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B | Done |  | supplier code & name required
KIT plan | Users | Heading
No option to upload fortnight plan twice in a month | A,B | Done |  | OK
Replace "File name/Material name/Supplier name" input box with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
No need of supplier search and material search on portal - Common data for all suppliers | A,B,S | Done | Priyanshu | ok
After taking any action on portal (Approval / Deletion)- Every time update required on portal due to this we have to reselect the supplier or material. Why can't we do multi selection of files and take action all together. | A,B | Out of Scope |  | Not possible in current functioning
Before Uploading file name not visible - so not possible to judge which file is going to update on portal | A,B | Done | Aayushi | ok
Complete uploaded data of suppliers need to visible after entering as Admin & Buyer and if we want to see particular supplier details then supplier search is required. | A,B | Done |  | supplier code & name required
Pre-dispatch Information (Observations) | Users | Heading
Selection of date not available for supplier while declaring the stock. | A,S | Done |  | File ok but in downloading template time is not required
No linkage of daily schedules in template, supplier unable to get the dispatch information of parts. | A,B,S | Done |  | ok
Template downloaded is not having complete information as in SOW | A,B,S | Done |  | Material description is not there in downloaded template
Replace "File name/Material name" with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
Remove Select all button and display all suppliers files when supplier is not selected (by default) | A,B | Done | Anoop | ok
When supplier download template - They are having the complete details of requirement of that particular date | S | Done |  | ok
File upload without selecting supplier | A,B | Done | Aayushi | ok
Supplier not reloaded after file upload/delete | A,B | Done | Anoop | ok
No. of records displayed drop down list not working | A,B,S | Done | Naresh | removed - ok
4M Change Sheet (Observations) | Users | Heading
No colour coding while uploading data on portal | A,S | Done |  | ok
Replace "File name/Material name" with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
Remove Select all button and display all suppliers files when supplier is not selected (by default) | A,B | Done | Priyanshu | ok
Wrong template attached on portal | S | No Action; Need to discuss |  | Not working - Need to upload correct 4M change sheet template
File upload without selecting supplier | A,B | Done | Aayushi | ok
Supplier not reloaded after file upload/delete | A,B | Done | Anoop | ok
No. of records displayed drop down list not working | A,B,S | Done | Naresh | ok
Supplier Monthly Inspection Report (Observations) | Users | Heading
No colour coding while uploading data on portal | A,S | Done |  | ok
Replace "File name/Material name" with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
Remove Select all button and display all suppliers files when supplier is not selected (by default) | A,B | Done | Priyanshu | ok
Wrong template attached on portal | S | No Action; Need to discuss |  | Not working - Need to upload correct 4M change sheet template
File upload without selecting supplier | A,B | Done | Aayushi | ok
Supplier not reloaded after file upload/delete | A,B | Done | Anoop | ok
No. of records displayed drop down list not working | A,B,S | Done | Naresh | ok
Quality Manual (Observations) | Users | Heading
No need to create supplier search option - 1 time activity and common for all suppliers & Buyers | A,B,S | Done | Priyanshu | Not updated - supplier list still available
Replace "File name/Material name" with "Search" | A,B,S | Done | Priyanshu | Search field required to search data from entire data not from current page only | Out of scope,in sign off doc only mention search by supplier name
Remove Select all button | A | Done | Priyanshu | ok
No. of records displayed drop down list not working | A,B,S | Done | Naresh | ok
Remove drop-down supplier list | A | Done |  | Pending
Remove Actions/Status column | B,S | Done | Aayushi | Pending
Remove Supplier name column | A,B,S | Done |  | Pending
No need to mention supplier names | S | Done |  | Pending
FOC |  | Heading
No records to test on |  | No Action; Need to discuss |  | Need to upload data manually, so that we can check that process is working or not
After entering manaul data by infodart- need to check that suppier able to mention the remaning coloums or not |  | No Action; Need to discuss |  | Need to check after development and changes from Infodart | Done
Notifications | Users | Heading
No notification are going to add from admin | A | No Action; Need to discuss |  | ok
No pop up shown to supplier or buyer after update of notification | B,S | No Action; Need to discuss |  | ok
On trying to add a notification with end date before the start date, the message displayed is "Submitted successfully". Display following error message, "End date needs to be after the start date" and do not reload the page when OK is clicked after this. | A | Done | Aayushi | ok
Notification added on selecting "All Suppliers" is also visible to BSL users | A,B | Done | Anoop | ok
Vendor Questionnaire | Users | Heading
Not working as in Admin user ID | A | No Action; Need to discuss |  | Showing complete same data to Admin,supplier,Users
Change heading after entering in Questionnaire | S | Done | Priyanshu | ok
Limits of digits for telephone no are not fixed | S | Done | Priyanshu | ok
Limits of digits for telephone no are not fixed | S | Done | Priyanshu | ok
Supplier A10001, going to upload data again and again on portal. Once submit no option to edit by supplier | S | No Action; Need to discuss
If we choose YES in any field then unlock further fields | A,S | Done | Priyanshu
No option to upload data in Questionnaire | A,S | No Action; Need to discuss
Total Record count in paging | A,S,B | Done |  | ok
Mandatory fields need to update for Supplier | A,S,B |  |  | Need to check after development and changes from Infodart | Done
PHASE-I
Invoice Date does not accept future date |  | Done | Naresh | ok
Invoice POP Up show invoice detail as per Live |  | Done | Naresh | Position no & Schedule no still not available
Remove some extra column from Mail format (Quantity Order, Quantity Desc, Model Name,Batch Code, PO Date) |  | Done | Naresh | Invoice No & Invoice Date mis-match
CGST showing wrong amount on Supplier Invoice Detail |  | Done | Naresh | ok
Replace the text View to Bincard |  | Done | Naresh | ok
Remove Contract No column from Barcode detail |  | Done | Naresh | ok
Increase Barcode image height |  | Done | Naresh | Need to check for scanning
New Observations_15.11.2018
Buyer Association - No change / delete / edit option for mapping | A |  |  |  | Done
After completing the schedule on portal - schd. Lines not deleted | S |  |  |  | Done
All invoice entries showing double entry | S |  |  |  | Done
No delete option after creating of invoice - Same required as Phase-1 | S |  |  |  | Done
Important - All existing phase 1 modules / reports running after giving the go live of phase-II coz Schd v/s delivery report not visible on UAT, GRN details , Rejection details, Rescheduling of schedules, Stock declaration by suppliers | A,B,S | Most Critical Point |  |  | Done
Data delete cycle as per the SOW - even not folowing in phase-1 schedules not auto deleted on LIVE portal | A,B,S
New Observations_20.11.2018 (From Quality Dept)
Vendor Rating
Supplier Name Missing in report and display on portal | A,B,S |  |  |  | Done
4M change Sheet & SMIR Report :
No direct option for rejecting the uploaded data from suppliers. First we have to approve and then we have reject option. We have to change this in portal. | A,B |  |  |  | Done
Colour coding (Red / Green) - make it more visible, now not visible properly in portal. | A,B |  |  |  | Done
Supplier don’t have authority to upload more than 1 data in a month. Once BSL user had taken any decision of either approval or rejection then only after rejecting the data supplier able to upload new report on portal. | A,B |  |  |  | Done